## Summary
| Category Name | Total Use Cases | Pending Requirement Clarification | Pending on Tech | Pending Priority | Description
C1 | Functionality/User Journey Broken | 4 | 4 |  |  | Broken Use Case or functionality error
C2 | Incomplete/Missinformation for the User | 1 |  |  | 1 | Misinformation leading to User experience impact
C3 | Incomplete Error Mapping | 1 |  | 13 |  | Backend error code mapping againt every inctance of a use case in Consumer app
C4 | UI Improvements | 1 |  |  | 2 | User Interface Improvements of Consumer App
C5 | Business Agility | 7 | 1 |  | 6 | Enhancements that require continuous, and systematic evolutionary adaptation for gaining and maintaining competitive advantage.
C6 | App Performance | 9 |  | 5 | 4 | Consumer App performance on a mobile device under various loads and circumstances
|  | 23 | 5 | 18 | 13 | Total
| Progress status | Use Case
| Included in Sprint 2.0 | 3
| Included in Sprint 1.8 | 1
| Included Sprint 1.9 | 5
| Discussion planned with Business | 7
| Internal Tech discussion in progress | 6
| R&D session planned | 1
| Grand Total | 23

## Details
S# | Epic | Use Case | Category | Description of the problem | Jira Story | Status | Status Details | Severity | Progress status
1 | Promotions | Viewing a Promotion | Incomplete/Missinformation for the User | The expired promotions shows days as Negative | JCP-1062 | To-do | Pending Priority | S2 - User Impacted | Sprint 1.9
2 | Money Treansfer | IBFT | App Performance | Bank list takes time to load in the app | JCP-1063 | To-do | Pending on Tech | S2- User Impacted | Sprint 1.9
3 | Promotions | Viewing Promotions from Drawer | UI Improvements | The description of the promotions show in half of the screen | JCP-1064 | To-do | Pending Priority | S3- UI related | Sprint 1.9
4 | Home Screen | Home Screen Banner | Business Agility | The promotion banner on the home screen is not changeable from the backoffice | JCP-1065 | To-do | Pending Priority | S3 - UI related | Discussion planned with Business
5 | Home Screen | Home Screen Banner | Business Agility | Home screen banner redirection is hardcoded | JCP-1066 | To-do | Pending Priority | S3 - UI related | Discussion planned with Business
6 | Guest Mode | Partial Guest mode does not work properly | Functional/User journey broken | Many use cases in the app do not work on partial guest mode | JCP-1067 | To-do | Pending Requirement Clarification | S1- Journey Broken | Internal Tech discussion in progress
7 | QR Scan | QR Scan is slow due to extra irrelevant information to the user | Business Agility | While scanning QR, we show the user previous scans that he/she has done, which are of no use to the user | JCP-1068 | To-do | Pending Requirement Clarification | S2- User Impacted | Spint 2.0
8 | Mobile Bundles | Bundles loader/search issue | App Performance | Jazz/OMNO bundles display takes time to load | JCP-1069 | To-do | Pending on Tech | S2- User Impacted | Sprint 1.9
9 | Transaction History | Haphazard behavior of transaction history | App Performance | Transaction history take time to load | JCP-1070 | To-do | Pending on Tech | S1- Journey Broken | Internal Tech discussion in progress
10 | Transaction History | History does not appear randomly | App Performance | Missing Transaction hisotry | JCP-1071 | To-do | Pending on Tech | S1- Journey Broken | Internal Tech discussion in progress
11 | Multipayment | Deposit via other debit card broken journey | Functional/User journey broken | Deposit via other debit card journey is beoken | JCP-1072 | To-do | Pending Requirement Clarification | S1- Journey Broken | Discussion planned with Business
12 | Other Payment | Multiple screens missing heading and Sub heading | Business Agility | Multiple screens on the app are missing headings and sub headings | JCP-1073 | To-do | Pending Priority | S3 - UI related | Internal Tech discussion in progress
13 | Home Screen | User logs out when native back is pressed on the phone | App Performance | User logs out when native back is pressed on the phone | JCP-1074 | To-do | Pending Priority | S3 - UI related | R&D session planned
14 | Invite and Earn | Invitee list does not gets updated | App Performance | Invitee list on invite and Earn does not gets updated | JCP-1075 | To-do | Pending Priority | S2- User Impacted | Internal Tech discussion in progress
15 | Deposit via Debit Card | OCR scanning has multiple issues | App Performance | OCR behavior is inconsistent in the app | JCP-1076 | To-do | Pending Priority | S3 - UI related | Discussion planned with Business
16 | Promotions | Share option does not work | Functional/User journey broken | Share option in the promotions screen does not work | JCP-1077 | To-do | Pending Requirement Clarification | S2- User Impacted | Sprint 1.9
17 | Notifications | Notifications do not change the state to "read" | Business Agility | Once a notifications is opened, it does not change the status | JCP-1078 | To-do | Pending Priority | S3 - UI related | Spint 2.0
18 | Request Money | Request Money attahment does not show on the app | Functional/User journey broken | The attachment in request money does not show to the user | JCP-1079 | To-do | Pending Requirement Clarification | S2- User Impacted | Discussion planned with Business
19 | Notifications | Toast UI of notification is not as per Design system | Business Agility | Toast UI of notification is not as per Design system | JCP-1080 | To-do | Pending Priority | S2- User Impacted | Spint 2.0
21 | Receipts | Incorrect Information on multiple receipts | App Performance | Incorrect Information on multiple receipts | JCP-1082 | To-do | Pending on Tech | S2- User Impacted | Discussion planned with Business
22 | Invite and Earn | Multiple Invites failure | App Performance | Multple invite send failure | JCP-1115 | To-do | Pending Priority | S2- User Impacted | Internal Tech discussion in progress
23 | QR Scan | Repayment on recent QR scanned | Business Agility | repayment on previously scanned QR failure. | JCP-1116 | To-do | Pending Priority | S2- User Impacted | Sprint 1.8
24 | Error Mapping | Use case wise FE msg fixing | Incomplete error mapping | Use case wise FE msgs fix | JCP-1117 | To-do | Pending on Tech | S3 - UI related | Discussion planned with Business
25 | QR Scan | Insufficent balance in QR | Business Agility
Sender bank title fetch sende szero hence the reciver account reciveing limit can not check.
topup - and if the customer is on data , balance goes down nd the bundle sub fails.

## JazzCash Epic's
Jazz Cash Consumer App
Epic | User Stories
Registration | Create a new JazzCash account
Guest Mode | Pure Guest Mode
Partial Guest Mode
Login | Login Customer
Biometric Login | Login Via Fingerprint
Home Screen Coach Marks | Onboarding Tutorials
Forgot MPIN | Create MPIN
Forgot MPIN
Balance Refresh | Balance Load & Refresh
Profile Picture | Update Profile Picture
Remove Profile Picture
Manage Email | Add Email
Manage MPIN | Edit and Change MPIN
CNIC Expiry | User CNIC Expiry
Profile Name | Manage Profile Name
Add Money Debit Card | Deposit via debit Card
Request Money | Add Request Money
Ready Cash | Repay ReadyCash
Add money via ReadyCash
Add Money Via Bank | Deposit Money Via Bank Account - Tutorial
Jazz Cash Agent | Locate and add money via Agent
Account Upgrade | Upgrade account via nearby Agent
Transaction History | Transaction History Review
Sent Transactions
Received Transaction
Account Limit | Daily Limits Updates
Monthly Limits Updates
Yearly Limits Updates
Account Statement | Last Financial Year
Date Picker
Last Month
Financial year to date
Email PDF
My Approval | Pending approval
History
Minor Account | Create new Minor Account
Terms and conditions
Redeem Rewards | Redeem Cashback Reward
Cards and Link Accounts | Jazz Cash Debit Card
Linked Cards and other Bank Accounts
Biometric Permission | Enable Biometric
Jazz Cash Keyboard | Prepaid Load
Transfer to Bank
Transfer to Jazz Cash
All Jazz Cash Services
Jazz Cash Transfer | Customer to Customer
Transfer to non-jazz Cash
Bank Transfer | IBFT
CNIC Transfer | Send money to CNIC
Other Wallet Transfer | Easypaisa
Upaisa
Konnect
Payoneer | Transfer Fund
Link / D-Link account
Create a Payoneer Account
Raast | Send Money to IBAN
Send Money to Raast ID
Link / D-Link account
Money Transfer
Add beneficiary
Utility Bills | My Favorites
Electricity
Gas
Water
Internet
Telephone
Prepaid Load | Jazz Load
Ufone Load
Zong Load
Telenor Load
Post Paid Load | Jazz Load
Ufone Load
Zong Load
Telenor Load
Mobile Packages | Jazz Packages
Ufone Packages
Zong Packages
Telenor Packages
Mutual Funds | Account Mutual Funds
Credit Card Payment | All payments via Credit cards
Health Insurance | Subscription of the plans
Life Insurance | Subscription of the plans
Jazz Cash Debit Card | Order a New debit Card
Make a Transaction via Card
Card Management
Order a Paypak Card
Virtual Card
Play & Win | Play games and win rewards
Invite and Earn | Invite Friends
Track Invitees
M-Tag | Topup on M-tag
Bus Tickets | Purchase bus tickets
Education | School fees
College Fee
Coaching Centers
Universities Fee
Entry Test Fee
Daraz Wallet | Top-up Daraz Wallet via jazz cash
E-vouchers | Buy E-Vouchers
Government Payments | Pay Government Payments
Traffic Challan | Punjab Traffic Challan
Islamabad Traffic Challan
Online Vouchers | Pay Online Via JazzCash
Loan Repayment | Repay Government Loans
Donations | Donate via Jazz Cash
Nadra | Covid Payment
Corporate Payments | Corporate Companies Bills
AlaCart Shopping | Buy Products
Pompak | Financial Literacy
Locators | Search Agent locators / Maps
Scan QR | pay Bill via Scan QR
Pay Bill via Till ID
Search | App Features Search
Promotion | Promotion Banners
International Payment Request | International Payment via Payer
Receipts | Transactions Receipts
Notifications | All Notifications
Edit Home Screen | Edit Preferences
Top Picksw | Home Screen Top picks for user
Latest Updates | Home Screen Banners For Updates
Logout | App Logout
App Version Details | Jazz Cash App Version Details
App Permissions | Permission to access the device details/features
Maps | Address Update
Locations / Agents